## Sheet1
RISK (exposure)
Probability (of occurrence) |  | 1.Slight | 2. Moderate | 3. High
1. Very Unlikely
| 2. Possible |  | 3,4,5 | 1,2
3. Expected
| Risk | Description |  | Probability (1-3) | Exposure (1-3) | Contingency Plan
| 1 | Technical Complexity and Tool Development Challenges |  | 2 | 3 | Develop a modular approach to building the tool to isolate complexities, ensuring parts of the tool can progress without being hindered by others. Invest in additional research and development resources to address technical challenges as they arise.
| 2 | Validation and Accuracy Assessment Difficulties |  | 2 | 3 | Establish a clear validation framework with input from multiple experts to ensure diverse perspectives on accuracy. Plan for additional rounds of validation and involve the sponsor in early stages to confirm the validation approach is sound.
| 3 | Research Paper Development Delays |  | 2 | 2
| 4 | Project Management and Coordination Issues |  | 2 | 2
| 5 | Dependencies and Third-Party Collaborations |  | 2 | 2